## Sheet1
Sr no | Points | Resource | Remarks
1 | Claim Processing > Claim entry > Insured detail tab > Name of insured is also required. |  | Review Insured Tab after these points get finished
2 | Claim Processing > Claim entry > insured detail tab >In case of Above FCL , Requested sum , Approved Sum & pending Sum is also required. |  | Identical to point 7 | Add UW, Exclusion and Decision tabs in Claim
3 | Claim Processing > O/S Reserve > Update button is showing some error.
4 | Claim Processing > claim Entry > Claim benefit tab > previously settled Amount is also required here. Sum Insured amount should be auto fetched (in greyed out) |  | if item nm and policy nm is same but different benefit code. Take out the settled sum benefit wise
5 | Claim Processing > Claim entry > Policy detail tab > PSS report & Policy attachment is also required . |  | Cover in pt 7
6 | Claim Processing > claim entry > Policy detail (sub tab) is required beside Insured detail. |  | Cover in pt 7
7 | Claim Processing > claim entry > policy detail > UW decision is also required |  | Same as UW decision tab of policy for single person. | Cover in pt 7. We would haeve a main tab called Policy detail where all these 4 tabs would lie. Document printing
8 | Approved Sum insured - Settled = Claim amount (By default) for each benefit.
9 | Claim Processing > O/S Reserve > "Post" button is required in update mode .
10 | Zeal financials > Period setup > data entry portion is showing (from date) twice. Make it ( From date & To date)
11 | Policy Issue date will be locked & if system date is in close period then it will be last date of open period. Claim revision date & Claim settlement date will be same in control. |  | By default, current date
12 | IFRS Date (Input) on doc entry is required (it will be Open date)
13 | Ref no & issue date will be revised at the time of Posting on the logic of point 11.
14 | Doc no will be generated at the time of posting for Policy, Quotation, Alteration & Endorsement
15 | Exclusion & condition tab should also be visible in claim Processing (in Policy Detail Tab) |  | cover in pt 7
16 | Insured person detail of doc entry should be visible in claim processing (insured detail tab) |  | cover in pt 1
17 | Claim benefit & Reserve distribution > Auto Benefit amount will be fetched here and should be same as sum insured |  | sum insured - settled amount
18 | Appoint investigator on the claim. Appointment date, Name & attachment option will be required here. Change claim status to Investigation |  | New Investigator Tab | Name from service provider | When Investigator is created, Claim status would change to Investiagtion
19 | Report receiving date on investigator tab. Change status to Assesement. |  | Attachment/Report recieveing date option will be enable on update | As soon as Report is attached, that record will be locked. And claim status will be changed to Assesment. And Claim Investigator cannot be changed. Vice versa when claim status is Investigation, no claim tab can be changed. Neither delete
20 | In assessment tab, assemement date, notes , attachments option , take decision of reinvestigate or send to comitee will change claim status to comette decision. Also show benefit wise distribution and allow to change value and enter comments for each benefit. |  | New tab. When option is reinvestigate, claim status change to Invesitgation again | Options; Reinvestigate, send to committeee, Assessed | In case of Assessed, an option will be enable to create settlement. Claim Settlement will be enabled if it is assessed. | Claim Benefit can not be updated when claim status is pending Investigation or pending committee decision. | Settlement can not be updated when claim status is pending Investigation or pending committee decision.
21 | after assessment, it can be reinvestigate, sent to comitee , proceed for settlement. |  | cover in 20
22 | Add two tabs on claim processing > "Doc required base on loss type" with attachment option, received date and option to mark status, default requirement will be autoinserted and option to add more from the list attached for loss type and not already attached in claim & "claim checklist base on loss type" with option to mark complete. |  | if status is not complete, we will not let claim processing move further. Keep in mind, all the mandatory marked document must be atttached
23 | roles based security, list of restrictions and permissions required from 5PLR | 5PLR
24 | Unless status is investagion, no settlement would be allowed. |  | covered in 20
25 | claim activity history. Show Audit trails of all activities on calim done date wise |  | Create a table for logging claim information. When it was investigarted, processed etx.
26 | reserve lock option and separate option for posting role based.
27 | add payee type, as Policy Holder, Hospital (incase of health), nominee, beneficiary , insured ( for health) field in settlement tab |  | payee name txt field will be removed
28 | beneficiary and Nominee will be added via endorsement nonfancial and then it will be available on settlement screen.
29 | generate payment installment schedule with equal amounts in case of monthly / weekly based claims for any settlement. And book due payments in GL only based on daily schedule. |  | settlement child ¦
30 | show claim payment basis separate card below benefits grid for row click of benefit on claim benefit tab for each benefit. |  | Show claim compensation basis. Same as Document Entry. The only difference is fields will be readonly.
31 | all endorsement impact will be taken upto incident date.
32 | for death claims, only beneficiary / nominee endorsement should be allowed.